## Sheet1
GAP ANALYSIS TEMPLATE
Project Name |  | Timesheet Tracking System |  |  |  | Project Id | A-12583
Responsible |  | Emily, Alex, ExcelLog |  |  |  | Date | 2025-02-02
Project Objective |  | To add new functionalities to the existing time tracking system to make it more user friendly and easy to use
Sr No. | Current State |  | End Goal | Gaps | Implications |  | Recommendations | Timelines
1 | Timesheets need to be updated manually every week |  | Provide users with a feature to copy previous timesheets to save time | No "Copy from" button available in the current system | Current process of manually updating timesheets is time consuming |  | Provide "Copy from" button in the timesheet to enable users to copy any previous week's timesheets and save time | 2018-03-15
2 | Leaves updated in the timesheets do not reflect in the HR leave system |  | To have a linked system | No syncing between the two systems | Leaves not being updated either in timesheets or on the leave system |  | Link the timesheet system to the HR leave system | 2018-04-01
3 | Managers have to approve timesheets for their team members and cannot delegate to others when out of office |  | Enable managers to Delegate the timesheet approvals for their team members | No approval delegation feature | Timesheets not getting approved when the manager is not at work |  | Provide "Approval Delegation" tab to delegate the timesheet approvals to other members in the manager's absence | 2018-04-30
4
5
6